## Sheet1
BUG NAME | PRIORITY | STATUS | NOTES | Solution
Map Event causing crash | high | in progress | During Mapevent at the DOACTION state of a players turn, the game seems to freeze.
GUI not loaded after reload | medium | completed | Transition from Main Menu to Arena01 the first time works well. After game condition reloads Main Menu, arena01 does not load properly. | Cleaned the tile dictionary before initialising the tile manager.
Die not being seeded properly | low | completed | Dice roll does not seem to be random when used for player's roll in their turn. | Added a Reseed function for the die.
Resources not loading | high | completed | Resources do not visually load in build version | Resource's Z position was behind the background and thus wasn't being rendered. The Z position was changed to fix this so its above the background but behind the player.
Solo play does not work | medium | in progress | Currently only multiplayer is supported
No defined end game | high | in progress | Hit "Q" to quit between player turns, but needs real end.
Camera is static and not following the player | high | in progress | Temporary fix is to zoom the camera out to see the whole map. The default value for camera size is 5.
We are using Excel because for the following reasons:
+ Excel provides simple features which all teammates understand how to use.
+ Conditional formatting allows color coding of types of bugs for better tracking.
+ All teammates have access to the program.
Bug Name: (Short and Concise)
Types of Priority: { HIGH, MEDIUM, LOW }
Types of Progress: { IN PROGRESS, COMPLETED }
Notes: Describe how or when the bug can be replicated.
Solution: Describe what was done to solve the bug.